## Project Grading Policy
Project Checklist and Grading Policy
PROGRESS
No | Deliverables | Presented in Class | MAX Points | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 1 | Team 2 | Team 3 | Team 4 | Team 5
1 | Business Case | NO | 6 | PROGRESS Team 1: 6; PROGRESS Team 2: 6; PROGRESS Team 3: 6; PROGRESS Team 4: 6; PROGRESS Team 5: 6
2 | List of Customer needs | NO | 4 | PROGRESS Team 1: 4; PROGRESS Team 2: 4; PROGRESS Team 3: 4; PROGRESS Team 4: 4; PROGRESS Team 5: 4
3 | List of Internal User needs | NO | 4 | PROGRESS Team 1: 4; PROGRESS Team 2: 4; PROGRESS Team 3: 4; PROGRESS Team 4: 4; PROGRESS Team 5: 4
4 | BRM Diagram, SIPOC, User Roles | YES | 5 | PROGRESS Team 1: 5; PROGRESS Team 2: 5; PROGRESS Team 3: 5; PROGRESS Team 4: 5; PROGRESS Team 5: 5
5 | Context Diagram; System Interface Table | YES | 3 | PROGRESS Team 1: 3; PROGRESS Team 2: 3; PROGRESS Team 3: 3; PROGRESS Team 4: 3; PROGRESS Team 5: 3
6 | Architecture Diagrams (Logical, Process views) | NO | 3 | PROGRESS Team 1: 3; PROGRESS Team 2: 3; PROGRESS Team 3: 3; PROGRESS Team 4: 3; PROGRESS Team 5: 3
7 | Functional Decomposition Diagram, Fishbone Diagram | NO | 2 | PROGRESS Team 1: 2; PROGRESS Team 2: 2; PROGRESS Team 3: 2; PROGRESS Team 4: 2; PROGRESS Team 5: 2
8 | User Stories with columns "Constraints", "Exceptions" | YES | 6 | PROGRESS Team 1: 6; PROGRESS Team 2: 6; PROGRESS Team 3: 6; PROGRESS Team 4: 6; PROGRESS Team 5: 6
9 | Road Map (S1, S2, S3) | YES | 3 | PROGRESS Team 1: 3; PROGRESS Team 2: 3; PROGRESS Team 3: 3; PROGRESS Team 4: 3; PROGRESS Team 5: 3
10 | RTM, RCT - Planning (S1, S2, S3) | YES | 6
11 | Supplementary Requirements (crosscuts, ET Table in RCT) | NO | 4
12 | UML Use-Case Diagrams | NO | 2
13 | UML Activity Diagram | YES | 2
14 | UML Class Diagrams | NO | 2
15 | UML Sequence Diagrams | NO | 2
16 | Tasks for User Stories (S2, S3) | NO | 6
17 | Burndown charts (S1, S2, S3) | YES | 4
18 | Dataflow Diagrams (logical, physical) | NO | 3
19 | ER Diagrams (conceptual, logical) | YES | 3
20 | Table Specifications (Data Dictionary) | NO | 2 | PROGRESS Team 2: 2
21 | Source Code sample (part of Demo) + Git repository PP slides (images) | NO | 4
22 | Jenkins Demo (recorded) | NO | N/A
23 | Jenkins Progress Report (S1, S2, S3) | YES | N/A
24 | Acceptance Tests (Test Design, Test Cases) | NO | N/A
25 | Class Presentation PowerPoint | NO | 4
26 | Class Presentation, Application Demo (recorded) | YES | 20
|  | TOT: | 100 | PROGRESS Team 1: 36; PROGRESS Team 2: 38; PROGRESS Team 3: 36; PROGRESS Team 4: 36; PROGRESS Team 5: 36

## Team 1 CORP Matrix Example
Project Preparation Phase
Team 1: Individual Contribution Matrix
| C - Contributor O - Owner PR - Peer-Reviewer | Member Name 1 | Member Name 2 | Member Name 3 | Member Name 4 | Member Name 5 | Member Name 6 | Member Name 7 | Member Name 8 | Member Name 9 | Member Name 10
1 | Produce Business Case |  |  |  | O
2 | Collect Customer needs |  | O | PR | O | [5 empty] | C
3 | Collect Internal User needs |  | O | PR | C
4 | Produce Business Requirements Document |  |  | C,PR | [5 empty] | C
5 | Produce BRM/SIPOC Diagrams, identify User Roles | C |  | PR |  |  | O |  |  | C
6 | Establish DEV, QA environments in AWS/EC2 |  |  | O |  |  | PR | C
7 | Architecture Diagrams (Logical, Process views) | [9 empty] | O
8 | Functional Decomposition, Fishbone Diagram | PR |  |  | C,PR |  |  |  |  | O
9 | Context Diagram; System Interface Table | O | [7 empty] | PR
10 | Implement Application Homepage | [5 empty] | PR
11 | Implement Jenkins deployment pipeline to DEV environment |  |  |  | PR

## Prep - Contribution Matrix
Project Preparation Phase
Team N: Individual Contribution Matrix
| C - Contributor O - Owner PR - Peer-Reviewer | Mudra Koradia | Brinda Patel | Avadhi Shah | Sushanth Nandeti | Dhwarakesh Shankar | Ruthwik Mamidala | Sivasankaran Kaleeswaran | Ruchitha Thaniparthy | Jalak Gevariya | Rahul Cholleti
1 | Produce Business Case |  |  | O | C | PR | [5 empty] | Done
2 | Collect Customer needs |  |  |  | C |  | C | O |  |  | PR | Done
3 | Collect Internal User needs | O | PR | C | [7 empty] | Done
4 | Produce Business Requirements Document |  |  | PR |  |  | O |  | C |  |  | 2nd
5 | Produce BRM/SIPOC Diagrams, identify User Roles |  |  |  |  | C |  |  | C | PR | O | Done
6 | Establish DEV, QA environments in AWS/EC2 |  | C |  | PR | O |  | C |  |  |  | Done
7 | Architecture Diagrams (Logical, Process views) | PR | O | C
8 | Functional Decomposition, Fishbone Diagram | [5 empty] | PR |  |  | O | C
9 | Context Diagram; System Interface Table | [5 empty] | PR |  | O | C
10 | Implement Application Homepage |  |  |  | O |  |  | C |  |  | PR
11 | Implement Jenkins deployment pipeline to DEV environment |  | O |  | PR | C |  | C
| Produce a Homepage sketch | O | [9 empty] | Done
| Start developing Homepage |  |  |  | O | [6 empty] | Done
| Create projects in GitHub for code management; Watch Git tutorial on YouTube | [6 empty] | O |  |  |  | Done
| RCT (1st Tab, Functional Decomp): define each module purpose | O | [9 empty] | Done
| Include Business Requirements in RCT/RTM Tab, start identifying application core features |  |  |  | O | [6 empty] | Done
| Database creation and migration |  |  | O | [7 empty] | Done

## Sprint 1 Contribution Matrix
Sprint 1
Team N: Individual Contribution Matrix
| C - Contributor O - Owner PR - Peer-Reviewer | Mudra Koradia | Brinda Patel | Avadhi Shah | Sushanth Nandeti | Dhwarakesh Shankar | Ruthwik Mamidala | Sivasankaran Kaleeswaran | Ruchitha Thaniparthy | Jalak Gevariya | Rahul Cholleti
1 | Produce RTM | PR |  |  | O |  |  | C
2 | Produce RCT | C |  |  | PR | O | [6 empty] | ⁠1. Functional Decomposition produced | Rahul
3 | Produce Entitlements Table | PR |  |  | C |  |  | O |  |  |  |  | 2.⁠ ⁠Context Diagram produced | Ruchitha
4 | Define User Stories |  |  | O |  |  | C | PR |  |  |  |  | 3.⁠ ⁠Product Backlog: RCT Produced | Mudra
5 | S1: Dataflow Diagrams (2) (Logical, S1 scope) |  |  |  |  | PR |  |  |  | O | C |  | 4.⁠ ⁠Project RoadMap (S1, S2, S3) | Avadhi
6 | S1: Burndown Chart (in Excel) | O | C | [5 empty] | PR |  |  |  | 5.⁠ ⁠Jenkins Deployment Pipeline created and tested | Brinda
7 | Jira: populate User Stories | [6 empty] | PR | C |  | O
8 | Jira: setup and update Kanban Board |  |  |  |  | PR | O |  |  | C
9 | S1: UML analysis diagrams (use case diagram) |  |  | PR |  |  | C |  |  | O
10 | S1: UML analysis diagrams (activity diagram) |  |  | PR |  |  | C |  |  |  | O
11 | S1: Implement User Stories | PR | C |  | C | C |  | O | C |  | C
| C - Contributor O - Owner PR - Peer-Reviewer | Mudra Koradia | Brinda Patel | Avadhi Shah | Sushanth Nandeti | Dhwarakesh Shankar | Ruthwik Mamidala | Sivasankaran Kaleeswaran | Ruchitha Thaniparthy | Jalak Gevariya | Rahul Cholleti
| Create and distribute a Daily Plan for the week | O
9 | UML analysis diagrams (use case diagram) |  |  | PR |  |  | C |  |  | O
10 | UML analysis diagrams (activity diagram) |  |  | PR |  |  | C |  |  |  | O
| S1: Slack communication - build deployed to QA environment |  | O |  |  | C
| S1: Jenkins - Slack notifications, deployment to QA |  | O |  |  | C | [5 empty] | Jenkind Demo
| S1: Perform Exploratory Testing; report defects | All | All | All | All | All | All | All | All | All | All | Everybody has to preform this
| S1: updated Burndown Chart (in Excel) | O
| S1: updated Kanban Board (in Jira) | [7 empty] | O |  |  | Jira Screenshot: Ruchitha
| S1: recorded Application Demo |  |  |  | O | [6 empty] | Applicaion Demo: Sushanth
| S1: Retrospective Report; discuss re-planning Sprint2 | C |  | O
| S1: Complete and agree to the Contribution Matrix (COPR) | O
| S1: Sprint1 Review Rehearsal | All | All | All | All | All | All | All | All | All | All | Presentation 25th
11 | S1: User Stories: Category Management – Add, Update, Delete. | PR |  |  | C |  |  | O
11 | S1: User Stories: Product Management – Add, Update, Delete. | PR |  |  | C |  |  | O
11 | S1: User Stories: Inventory Dashboard | PR |  |  | O |  |  | C
11 | S1: User Stories: Manage Product Stock Levels | PR |  |  | O |  |  | C
11 | S1: Delete Account | PR |  |  | O |  |  | C
| 1 | Avadhi
RoadMap
Explain the rationale how the team decided what to include in
Sprinti scope.
| 2 | Mudra
RCT Planning
Open the RCT composition view and explain the team's decision about which crosscuts to implement.
| 3 User Stories | Avadhi
Choose one story as example and explain it, in particular, Story Constrains and Exceptions.
| 4 | Mudra
BurnDown Chart
Explain the purpose of the chart and comment whether the team was on schedule to deliver Sprinti.
| 5 | Ruchita
Kanban Board
Explain the purpose of the Kanban Board and what it shows.
| 6 | Rahul
Activity Diagram
Explain the purpose of the diagram and the flow it shows.
| 7 | Jalk
Retrospective Report
Open Report and explain what worked well during the Sprint and what should be improved and how going forward.
| 8 Git Repository | Siva
Create just 1-2 slides and explain the repository folder structure.
Make sure you have the folder "Final Project Presentation".
| 9 | Dhwarkesh
Jenkins Demo
Record a short Demo (3-4 min) demonstrating a pipeline execution.
| 10 | Ruchita
Jira Demo
Create 2-3 slides showing stories, defects and a Kanban Board in the Jira project.
| 11 | Siva
Application Demo
Record a short Demo (3-4 min) demonstrating the stories implemented in Sprintl.
| 12 | Siva
ChatGPT
Create a Word document capturing the information from ChatGPT you used in Exploratory testing.

## Sprint 3 Contribution Matrix
Sprint 3
Team N: Individual Contribution Matrix
C - Contributor O - Owner PR - Peer-Reviewer
1 | S3: RCT - Planning (with Crosscuts)
2 | S2: Burndown Chart (Excel)
3 | S2: Kanban Board in Jira
4 | S3: List of Story Tasks
5 | S3: ER Diagrams (Conceptual, Logical)
6 | S3: Dataflow Diagram (logical, physical)
7 | S3: UML Class Diagram
8 | S3: UML Sequence Diagram
9 | S3; Implement User Stories
10 | S3: Acceptance Tests (Test Design)
11 | S3: Acceptance Tests (Test Cases)
12 | S3: Test Execution Log (execute formal testing)
13 | S3: Updated Jenkins Progress Report
14 | S3: Application Demo [recorded]
15 | S3: Jenkins Demo [recorded]

## Sprint 2 Contribution Matrix
Sprint 2
Team N: Individual Contribution Matrix
C - Contributor O - Owner PR - Peer-Reviewer
1 | S2: RCT - Planning (with Crosscuts)
2 | S2: Burndown Chart (Excel)
3 | S2: Kanban Board in Jira
4 | S2: List of Story Tasks
5 | S2: Dataflow Diagrams (2) (logical, physical)
6 | S2: ER Diagrams (Conceptual, Logical)
7 | S2: Database Table Specification
8 | S2: UML Class Diagram
9 | S2: UML Sequence Diagram
10 | S2: Updated Jenkins Progress Report
11 | S2: Implement User Stories
12 | S2: Application Demo [recorded]
13 | S2: Jenkins Demo [recorded]