## Daily Plan W6
Sprint 1: Daily Schedule, Week 6
Tasks | Tuesday -Oct 15 | Wednesday -Oct 16 | Thursday -Oct 17 | Friday -Oct 18 | Saturday -Oct 19 | Sunday -Oct 20 | Monday -Oct 21
S1: Implement User Stories | x | x | x | x | x | x | x
S1: RCT - Planning (with Crosscuts) | x | x | x | x
S1: Supplementary Requirements (crosscuts, ET in RCT) | x | x | x | x
Define User Stories with columns Constraints, Exceptions |  |  |  | x
S1: Dataflow Diagrams (2) (Logical, S1 scope) |  |  |  | x | x
S1: Burndown Chart (in Excel) | x | x | x | x | x | x | x
S1: Jenkins deployment to Dev, QA environments |  |  | x | x | x
S1: Jenkins - implement Slack notifications |  |  | x | x | x
Jira: populate User Stories |  |  |  | x | x
Jira: create RoadMap |  |  |  |  | x | x
Jira: setup and update Kanban Board |  |  |  |  | x | x
S1: User Stories - 04.01 Log In as User |  |  | x | x | x
S1: User Stories - 04.02 Log In as Admin |  |  |  | x | x | x