## Daily Plan W6
Sprint 1: Daily Schedule, Week 6
Tasks | Tuesday -Oct 22 | Wednesday -Oct 23 | Thursday -Oct 24 | Friday -Oct 25 | Saturday -Oct 26 | Sunday -Oct 27 | Monday -Oct 28
S1: UML analysis diagrams (use case diagram) | x | x | x | x
S1: UML analysis diagrams (activity diagram) | x | x | x | x
S1: Slack communication - build deployed to QA environment |  | x | x | x | x
S1: Jenkins - Slack notifications, deployment to QA |  | x | x | x | x
S1: Perform Exploratory Testing; report defects |  |  | x | x | x
S1: updated Burndown Chart (in Excel) | x | x | x | x | x | x
S1: updated Kanban Board (in Jira) |  |  |  |  | x
S1: recorded Application Demo | [5 empty] | x
S1: Retrospective Report; discuss re-planning Sprint2 |  |  |  |  | x | x
S1: print1 Review Rehearsal |  |  |  |  | x | x
S1: User Stories: Category Management – Add, Update, Delete. | x | x |  |  | x | x
S1: User Stories: Product Management – Add, Update, Delete. |  | x | x
S1: User Stories: Inventory Dashboard |  | x | x | x | x
S1: User Stories: Manage Product Stock Levels |  |  |  | x | x
S1: Delete Account |  |  |  | x | x