## Road Map
WHISK AND DRIZZLE
Application Modules | Feature Backlog | Story Points | Sprint 1 - 10/29/2024 | Sprint 2 - 11/19/2024 | Sprint 3 - 12/17/2024
01. Brand Visibility Management | 01.01 About Us Page | 2 |  |  | x
| 01.02 Our Craft Page | 2 |  |  | x
| 01.03 Social Media Campaigns | 2 |  |  | x
| 01.04 Email Promotions & News Letters | 2 |  |  | x
02. Product Interaction | 02.01 Browse The Product Variety | 3 |  | x
| 02.02 View Detailed Product Information | 4 |  | x
| 02.03 Add / Update / Delete / View Product to Cart | 4 |  | x
| 02.04 Personalize Orders | 3 |  |  | x
| 02.05 Product Rating and Feedback | 3 |  |  | x
03. Inventory Management (Admin) | 03. 01 Category Management – Add, Update, Delete. | 4 | x
| 03. 02 Product Management – Add, Update, Delete. | 4 | x
| 03. 03 Inventory Dashboard | 4 | x
| 03. 04 Manage Product Stock Levels | 3 | x
04. Account Management | 04.01 Log In as User | 3 | x
| 04.02 Log In as Admin | 3 | x
| 04.03 Easy SignUp | 4 | x
| 04.04 Delete Account | 2 | x
05. Streamlining Payments | 05.01 Saved Payment Methods | 3 |  | x
| 05.02 Secure Transactions | 3 |  | x
| 05.03 Multiple Payment Gateway | 4 |  | x
| 05.04 Email Confirmation | 4 |  | x
| 05.05 Adding Coupon | 4 |  | x
06. Enhancing User Support | 06.01 Contact Us Page | 2 |  |  | x
| 06.02 Order Traking Page | 3 |  |  | x
| 06.03 FAQ Sections | 2 |  |  | x
| 06.04 Return & Refund Policy | 2 |  |  | x
|  | VELOCITY: | 27 | 29 | 23